## Project Plan and Gantt
Project Name | Indie Game
Project Manager | Edward
Project Deliverable
Scope Statement:
Start Date | 2017-10-20
End Date | 2018-10-20
Overall Progress | 0%
Tasks | Responsible | Start | End | Days | Status
Production | Exellar | 2017-10-20 | 2018-07-20 | 273 | Complete
General Mechanics | Dev Team | 2017-10-21 | 2018-01-20 | 91 | Complete
First creation of Sprites | Dev Team | 2017-10-22 | 2017-10-30 | 8 | Complete
Room Design | Dev Team | 2018-04-20 | 2018-07-20 | 91 | Overdue
Basic Enemies | Dev Team | 2018-01-20 | 2018-04-20 | 90
Puzzle Creation | Dev Team | 2018-01-20 | 2018-07-20 | 181 | In progress
NPCs | Dev Team | 2017-11-20 | 2018-07-20 | 242 | In progress
Skill Trees | Dev Team | 2018-02-20 | 2018-07-20 | 150 | Not started
Weapons | Dev Team | 2018-01-20 | 2018-04-20 | 90 | Not started
User Interface | Dev Team | 2017-12-20 | 2018-07-20 | 212 | Not started
Story Creation | Ben | 2017-10-20 | 2018-07-20 | 273 | Not started
Dialogue | Ben | 2017-11-30 | 2018-07-20 | 232 | Not started
First Drafts of Music | Jimmy | 2017-10-20 | 2018-01-20 | 92
Background Music | Jimmy | 2018-01-21 | 2018-07-20 | 180 | Not started
Sound Effects | Jimmy | 2017-10-20 | 2018-07-20 | 273 | Not started
Interface Sounds | Jimmy | 2018-01-15 | 2018-02-20 | 36 | Not started
Post-Production | Exellar | 2018-07-21 | 2018-10-20 | 91
Launch | Exellar | 2018-10-20 | 2018-10-25 | 5